KAICIID Dialogue projects 2020

Mid-term Report

The mid-term report includes sections:

- Project description

- Implementation

- Activities Implemented so far

- Target group

- Efficiency

- Dissemination and sustainability

- Future steps

| # Description of the project |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project reference code |  | 8-CC4 |  |  |  |  |
| Name of the applying organisation / Individual / Group |  | Horn of Africa Aid and Rehabiliation Action Network – (HAARAN) HAARAN Kenya / Somalia programmes. |  |  |  |  |
| Country |  | Somalia |  |  |  |  |
| Reporting for the period: X to Y |  | 01/Sep/2020 to 31/Jan/2021 |  |  |  |  |
| Person responsible for the reporting |  | William Tolbert, Programs Director HAARAN Kenya /Somalia programs |  |  |  |  |
| Initiative Title |  | Tackling Religious Driven Violence Against Community In Somalia |  |  |  |  |
| Initiative objectives |  | The objective of the projects are : - Strenthen the community strucatures to be vaiable democratic structures that embrace good governance and encourage resprect for all. - To increase peace education targetting young people in community |  |  |  |  |
| # Implementation |  |  |  |  |  |  |
| # a-Implemented Activities so far |  |  |  |  |  |  |
| Activity | Type | Venue-Online tool |  | date |  | Trainer/Speaker and profile |
| 1 | Challenges or risk areas that affect peace in the context Somalia | - Focus group discussions with; - Five head tecahers in target patner sschools in Kimsayu ditrict - Parents, CECs and Relgiois leaders from each school community - Teachers in the five target schools |  | 12 to 17 October 2020 |  | Farhan Abdi , project officer for ADRA -Somalia based in Kimsayu |
| 2 | Cohort one Training Worshop for 25 Particpaitnat on Peace Building & Conflict Transformation. | Kimsayu Hotel Somalia |  | 18th to 22 October |  | William Tolbert Programs Director HAARAN Kenya/ Somalia Programs And Co facciliator with help of the MOE in Jubbland and SWS |
| 3 | Cohort two training Worshop for 25 Particpaitnat on Peace Building & Conflict Transformation | Kimsayu Hotel Somalia |  | 25 th to 28th Octobert |  | William Tolbert Programs Director HAARAN Kenya/ Somalia Programs And Co facciliator with help of the MOE in Jubbland and SWS |
| 4 | Cohort three training Worshop for 30 Particpaitnat on Peace Building & Conflict Transformation | Horyaal Hotel Somalia |  | 8th to 11th November |  | William Tolbert Programs Director HAARAN Kenya/ Somalia Programs And Co facciliator with help of the MOE in Jubbland and SWS |
| # b-Target Group |  |  |  |  |  |  |
| Total estimated number of beneficiaries as stated in the project proposal |  | 2000 and youths , 50 Teachers , 50 Communuty members / leaders and 20 ToTs |  |  |  |  |
| Real total number of beneficiaries for the initiative life time |  | More than 1000 youths and children have been reached indirectly, 60 teachers reached directly and 30 community memebrs and leaders reached also directly. |  |  |  |  |
| Categories (indicative) |  | Gender | Female |  | Male |  |
|  |  |  | 17 |  | 73 |  |
|  |  | Age Category | U18 |  | 19-30 |  |
|  |  |  | N/a |  | N/a |  |
|  |  |  | 31-44 |  | +45 |  |
|  |  |  | N/a |  | N/a |  |
| # In what way has the Project guaranteed diversity and inclusion in relation to participants, trainers and project management team ? As an organization, HAARAN belives in promoting diversity and inclution of all persons including persons with disabilities and women. HAARAN uses an a approach that allowed a tailored support aproach that brought on board all key stakholders involoved in the process of buiding sustanabtle peace in Jubbaland Somalia context. This included community made of parents, community leaders and religious leaders. We also had the teachers and head tecahers that were to work with youths and children directly on matters of relgious driven concflict something that affects more youths and children and adult. The training aimed to sensitize the communities on the need of peace through through myriad of interventions that include facilitating sensitation forums targeting relevant stakeholders, supporting life-skills trainng, and provision of relevant and appropriate IEC materials. The bullets below outlines the rationale of the partcipants and the role they are exprected to excute yond the training: Parents; Parents are the destny shapers of many young people thus they were trained so that they can influnece the children and youth growth and development in two levels namely at home levels and school levels since most children and young people are at risk.. Teachers /ToTs; The teachers and or trainers (local ToTs) will thereafter be assigned to every target community school and expected to monitor uptake of : {Tackling Religious Driven Violence Against Community In Somalia} intervention based on an issue guide that shall developed and shared by ADRA by february after the delibarative workshop planned for January. The project will collaborate with ministries of Education and ADRA Somalia a lead education agency to provide technical training to local schools based on the training content and issue guide. Other aspect of convsersation will include the physocial support and how to handle them in context of Somalia more so from the school point of view. In brief Teachers will encourage and monitor habits that leads to peace withing schools among children and youth.. Communuty leaders / Religious leaders; We did engange actively community and religious leaders in supporting peace at community with hopes that once we train them, the said leaders were well placed to lead the changes needed in commnunity thus moving forward they were tasked tasked to develop and implement a community based and managed action plan to address and prioritize peace with intrest of each of the schools targetted per commmunuty. We chose schools because schools are more of open space which look ideal to discuss senstsive subject such as {Tackling Religious Driven Violence Against Community In Somalia}. Line minitry / Goverment; Tackling Religious Driven Violence Against Community in Somali can only succed if proper linakges are framed between trained and active community and religious leaders and relevant government agencies and stakeholders. This is seen as a key step to start to tackle Religious Driven Violence Against Community In Somalia. Training local leaders and making them crucial voices to advocate for prioritization for child protection needs will ultimately mobilize more resources for the cause. Additionally, engaging local leaders and empowering them will result in the community leaders engaging as key stakeholders in future planning and implementation of child protection related programs; their participation is crucial because over time they will bring to the table community based, feasible and locally accepted interventions.. |
| # c-Modifications to the work plan (when relevant) |  |  |  |  |  |  |
| # Have you introduced any changes to the original work plan ? If yes, please explain No changes |  |  |  |  |  |  |
| # Efficiency |  |  |  |  |  |  |
| What are the real risks your project was subject to and in what way have you managed to overcome them? The main risk was security related risk in Somalia due to election and violene extrisms kind of actvity that are plenty in the region. HAARAN used partnership since we belive that peace building is an inclusive process. For effectiveness and risk mitigation, we ensured that the : . - Community Leaders, Elders and religious leaders lead from front since they play traditional role of conflict resolution. They are respected and sometimes revered and their decisions hold a lot of moral authority. - Government Administration also were involovle since they play a central role in overall administration of the area. Their role and capacity will enhanced the project outcome . - Religious Leaders- Among the Somalis, religion and culture are inseparable. Due to strict adherence to religion. Religious leaders’ place in the society is very high and any major decision affecting the society is reflected under religion. religious leaders will play a key role to avoid misconception |  |  |  |  |  |  |
| # In case there were unsolved challenges, please name them and describe the impact on the implementation of the project Nothing much so far save for it was not possible to have vurtual aproach due to poor connection in the region. We therfore opted to do safe remote aproach. |  |  |  |  |  |  |
| # Dissemination and sustainability |  |  |  |  |  |  |
| Please share with us the communication channels you are using to promote the project We use socaial media and community dialogue focrums including the community radio like kismayu and star fm |  |  |  |  |  |  |
| How did you manage to involve policy makers in the project? Consulatation of key policy makers in very cirical in Somalia contect thus to succeed we first had to involve the lead agency and line ministry to ensure that we get the buy in. In our case we worked mostly with lead agency incharge of education and the line minitry namely the ministry of education |  |  |  |  |  |  |
| Could you please list the dissemination material/activities implemented to guarantee the visibility of the initiative Basically we used T- Shirts and Banner , below are some photos of the phase one actions Please provide links and high quality photos https://drive.google.com/drive/folders/1mtRhKfrR3U0oGzn-3EPwRG2Nd-ck3Pu3?usp=sharing |  |  |  |  |  |  |
| # Future Steps |  |  |  |  |  |  |
| What are the remaining activities to be implemented and what are the dates you fixed for each? We have one core acvity that is tageting the religious leaders and orther stakholders and that is to take place in the first week of Janaury 2020. This forum will be kind of a dilogue and delibaration workshop geared towards developeing and issue guide. |  |  |  |  |  |  |